## Sheet1
1. Tarot Readings
A. Database & Deck Data
Microtask | Model | Context/Tokens | Notes/Factors
Fix and test DB seeding script (ESM/CJS/import/export) | Claude | 4-8K | Needs codebase context, error logs, testing.
Seed all 78 cards (full metadata, images, keywords) | Gemini | 3-8K | Use CSV upload/script. Swarm possible for rapid entry/validation.
Confirm deck data integrity (spot-check, output log) | Roo → Claude | 2-4K | Roo runs checks, Claude reviews/finalizes.
Add support for deck versions/custom decks (Phase 2) | Claude | 4-6K | Architecture/design, can split across sessions.
B. API & Backend
Microtask | Model | Context/Tokens | Notes/Factors
Ensure /api/tarot/deck returns full/correct data | Claude | 2-6K | API+DB context.
Add endpoints: draw, shuffle, save, get reading | Gemini | 3-8K | Batchable, can split by endpoint.
Error handling & validation | Gemini | 2-4K | Can swarm.
Logging: attempts/errors/analytics | Claude | 2-4K | Logging/analytics setup.
C. UI/UX
Microtask | Model | Context/Tokens | Notes/Factors
Wire frontend to backend | Claude | 4-8K | Full React context, keep in one session.
Implement true shuffle animation | Claude | 2-6K | Visual/UX focus.
Reading spreads (single/3/custom) | Gemini | 2-4K | Component logic.
Modal: flip, meaning, reversed | Claude | 2-4K | UX & accessibility.
Loading/success/error states | Gemini | 2-4K | Swarmable.
Mobile-first grid, touch UI | Claude | 2-4K | Layout/UX.
Journaling/notes per reading | Gemini → Claude | 2-4K | Backend (Gemini), UI (Claude).
D. Testing
Microtask | Model | Context/Tokens | Notes/Factors
E2E tests for full reading | Roo | 2-4K | Can be automated and validated by Claude.
API tests for deck endpoints | Gemini | 2-3K | Batchable.
Manual test log/screenshots | Roo | 1-2K | Scripted/manual output.
2. Astrology
A. Birth Chart
Microtask | Model | Context/Tokens | Notes/Factors
Location input (lookup/maps, TZ auto) | Gemini | 4-8K | Needs city DB, API config.
Date/time input, DST, TZ history | Gemini | 2-6K | Swarm for edge cases.
Ephemeris integration (Swiss Ephemeris/API) | Claude | 6-12K | Heavy context, reliable code.
Planet/body calculation | Claude | 2-8K | Detail, accuracy required.
House system selection | Claude | 1-2K
Wheel/aspect grid visualization | Claude | 4-8K | Needs design + code.
Export/share chart | Gemini | 2-4K | Simple export logic.
Accessibility for visuals | Claude | 1-2K
B. Transits/Progressions/Solar Returns
Microtask | Model | Context/Tokens | Notes/Factors
Current/future transits calculation | Claude | 2-6K
Overlay transits on natal chart | Claude | 2-4K
Progressions/solar return computation | Claude | 2-4K
Daily/weekly forecast module | Gemini | 2-4K | Text gen, summary.
C. Compatibility/Synastry
Microtask | Model | Context/Tokens | Notes/Factors
Dual chart input UI/backend | Claude | 2-6K | Session together.
Inter-chart aspects/synastry grid | Claude | 4-8K | Complex math, needs context.
Composite chart calculation | Claude | 2-4K
Compatibility summary/score | Gemini | 2-3K | Text gen, batchable.
D. Advanced Astro
Microtask | Model | Context/Tokens | Notes/Factors
Astrocartography/relocation | Claude | 6-12K | Advanced, heavy context.
Electional astrology UI/logic | Claude | 6-8K
Moon phase, retro, V/C tracking | Gemini | 2-4K | API lookup.
E. Testing & Logging
Microtask | Model | Context/Tokens | Notes/Factors
Validate output with reference charts | Roo | 2-4K | Automate/screenshot.
Edge cases: leap years, rare locations | Roo | 2-4K | Automated run, log.
Log every reading/request | Gemini | 1-2K | Batchable.
3. UI/UX & Galaxy/Starfield
Microtask | Model | Context/Tokens | Notes/Factors
Review CLAUDE_UI_UX.md, document reqs | Claude | 2-4K | Internal design session.
Audit/fix 3-panel & mobile layouts | Claude | 4-8K | Visual/React context.
Galaxy/starfield animated BG | Claude | 4-8K | WebGL/CSS expertise.
Mobile performance tests | Roo | 2-4K | Automated scripts.
Add aria/accessibility tags | Claude | 2-3K | Audit+fix.
Modal/page/card/chart animations | Claude | 2-6K
WCAG compliance audit | Gemini | 2-4K | Batchable, checklist.
Dark/light mode toggle | Gemini | 2-3K | Simple logic.
Document all gaps/schedule fixes | Claude | 2-3K | Output log.
4. Auth & User Management
Microtask | Model | Context/Tokens | Notes/Factors
Fix/test signup/login/OAuth (Supabase/Next.js) | Gemini | 2-4K | Parallelizable.
Session persistence/logout | Gemini | 1-2K
User profile fields | Gemini | 1-2K
RLS (Supabase) | Gemini | 1-2K
Password reset/email confirm | Gemini | 1-2K
Manual/E2E auth tests | Roo | 2-4K | Scripting.
5. Journaling, History, Personalization
Microtask | Model | Context/Tokens | Notes/Factors
Save readings (tarot/astro, dt) | Gemini | 2-3K
Tag readings w/ moods, notes | Gemini | 2-3K
Reading history/search/filter UI | Claude | 2-6K | Session with UI work.
User dashboard: stats, streaks, recs | Claude | 2-4K
Save last location/TZ for quick reads | Gemini | 1-2K
Prep for adaptive reader/agent | Claude | 2-6K | Early agent framework.
6. Notifications, Sharing, Social
Microtask | Model | Context/Tokens | Notes/Factors
Enable reminders (email/SMS/push) | Gemini | 2-4K | API setup.
Shareable reading links/images | Gemini | 2-4K
Community opt-in sharing | Claude | 2-4K
Referral system | Gemini | 2-3K
7. Infra, DevOps, Admin
Microtask | Model | Context/Tokens | Notes/Factors
Build/test/deploy pipeline | Roo → Gemini | 2-4K | Roo scripts, Gemini fixes.
Logs/alerts for critical errors | Gemini | 2-3K
Automated DB/media backup | Gemini | 1-2K
Admin dashboard (content, users) | Claude | 2-6K
Legal: privacy, terms, disclaimer | Gemini | 1-2K
8. Docs & Compliance
Microtask | Model | Context/Tokens | Notes/Factors
Update agent logs (CLAUDE.md etc) | Claude | 1-2K | Session-end routine.
Code comments/dev onboarding guide | Gemini | 2-4K
Complete README/setup docs | Gemini | 2-4K
Accessibility & GDPR/CCPA checks | Gemini | 1-2K | Checklist.
⚡ Session Grouping/Context
Group all UI/UX microtasks (per feature) into single Claude sessions to maximize continuity.
Assign backend/API microtasks in parallel sessions to Gemini for throughput.
Give all E2E/integration/manual validation to Roo, orchestrated by Claude (or Gemini if swarming).
Keep related subtasks (e.g., tarot deck seeding, deck API, deck UI wiring) in the same session if under 16K context.
When hitting token/context limits, checkpoint (log) and open a new, linked session—always outputting a summary.
⚡ Swarming/Agent Orchestration
Claude should define agent registry, roles, escalation rules, and swarming triggers (e.g., deck data entry, E2E batch tests).
Gemini is best for rapid, repeated content/code/script generation (swarm for CSV, batch endpoints).
Roo can swarm for multiple E2E/browser/device configs or for repeated logging and output checking.
All agents should log their actions and escalate blockers (e.g., Claude to Gemini/Roo or vice versa).
Summary Table (Sample, Tarot Only)
Microtask | Est. Time | Model | Session Strategy
DB Seed Fix | 20m | Claude | Full code context
Seed Deck | 30-60m | Gemini | CSV/script swarm
API Deck | 20m | Claude | API + DB session
UI/UX Wire | 45m | Claude | Single UI session
E2E Test | 30m | Roo | Scripted/batch